1. Determine the Input, Process and Exit criteria for each of the project
management processes in Tabular Form

Ans:

INITIATION PHASE
INPUTS	PROCESS	OUTPUTS
Interviews with customer and other key personnel / Strategic documentation / Customer literature / Lessons learned from previous projects performed for project sponsor	Interview Customer / Conduct Internal Research / Develop Solution and Requirements / Review Lessons Learned / Review Customer Requirements / Define Project Roles(Project Manager/Project Sponsor/Project Team Members) / Assemble Core Project Team / Develop High-Level WBS / High-Level Risk Assessment(Contingency plan) / Develop Cost Estimates / Develop High-Level Project Charter / Review with Owners for Approval	Opportunity Summary / Pre-Project Budget Worksheet / Opportunity Assessment Detail / Quality Assurance Template / High Level WBS / High Level Risk Assessment / Client Cost Benefit Analysis / Problem Identification / Proposal Checklist / Project Proposal Document / High Level Project Charter

PLANNING PHASE
INPUTS	PROCESS	OUTPUTS
High Level Project Charter / High Level Risk Assessment / Requirements Document	Conduct a Project Team Detailed Planning Meeting and Work Session / Develop the Detailed WBS / Develop The Responsibility Matrix(Who will be the reviewer,owner,approval) / Develop communications plan(reporting,documentation) / Risk Assessment and Management Planning / Define the HR skill requirement / Schedule preperation(task estimates,sequence tasks) / Develop cost management plan / Determine quality policy(Checklists,reviews) / Project procurement management / Obtain communication management plan approval / Finalize project charter / Conduct management review with owner / Develop baselines	Communications Plan / Project Charter / Resource Request Form / Project WBS / Requirements Traceability Matrix / Responsibility Matrix / Risk Management Guide / Project Notebook / Developing Task Worksheet / Project Schedule

EXECUTION PHASE
INPUTS	PROCESS	OUTPUTS
Project Team / Project WBS / Communication Plan / Risk Management Plan / Responsibility Matrix	Conduct tracking / Conduct project status meetings / Adjust schedules if there are change requests which can be tolerated	Current and Updated Project Schedule / Change Management / Quality Management / Phase Sign Off

MONITOR & CONTROL PHASE
INPUTS	PROCESS	OUTPUTS
Project Schedule / Project Notebook / Issues/Action Item Log	Check for scope boundary / Check on quality policy / Complete the phase sign off	•Progress and status reports / •Plan updates / •Risks registers / •Change requests / •Work products/deliverables

CLOSURE PHASE
INPUTS	PROCESS	OUTPUTS
Completed, up-to-date project schedules / All project documentation / Quality Checklists / Phase Sign-offs, as appropriate	Administrative closure / Survey the project participants(Performane evaluvations/Customer satisfaction survey) / Conduct post implementations review / Develop and record lessons learned / Send and archive documents to repository / Project celebration	Post Implementation Review / Performance Evaluations / Lessons Learned / Project Evaluation / Delivery of Final Documentation / Project Sign-Off / Customer Satisfaction Survey